## Sheet1
[6 empty] | Github Link: | https://github.com/la-mar/DDS_Case_Study_1
| Action Items: | Assigned To: | Rough Draft Due: | Revision #1 Due: | Final Revision Due: | Upcoming Meetings | Time (CST)
1 | Readme | TBD | 2018-06-24 |  | 2018-06-24 | 2018-06-19 | 6:30 PM - 8:30 PM
| - Discover what should go in the Readme |  |  |  |  | - Agenda:
| - Construct the Readme |  |  |  |  | - Complete first draft of report
- Complete first draft of presentation
2 | Project Intoduction | Matthew | 2018-06-19 | 2018-06-21 | 2018-06-24 | 2018-06-21 | 8:00 PM - 10:00 PM
- Write snippit/short paragraph
[6 empty] | 2018-06-24 | 3 hours
3 | Purpose of Study | Matthew | 2018-06-19 | 2018-06-21 | 2018-06-24
- Why was the analysis warranted / what larger question are we trying to answer
- What does the landscape of craft breweries look like in the US?
4 | R Code | Brock/Samuel
| - All R code required to answer 7 questions | Brock | 2018-06-19 | 2018-06-21 | 2018-06-24
| - Code comments/descriptions | Samuel |  | 2018-06-21 | 2018-06-24
| - Additional Plots (optional) | -
5 | R Markdown | Brock/TBD
| - Rmd Formatting | Brock | 2018-06-19 | 2018-06-21 | 2018-06-24
| - Plot Formatting | TBD
| - Write Plot Interpretations (imporant to Dr. Cheun) | TBD
6 | Presentation | Quinton | NA | 2018-06-21 | 2018-06-24
- Construction and Formatting
7 | Practical Answers to 7 Questions | Peter | NA | 2018-06-21 | 2018-06-24
8 | Project Conclusion | Quinton | NA | 2018-06-21 | 2018-06-24
- Write snippit/short paragraph
- Summarize all findings
- Describe the landscape of craft breweries
- Example conclusions:
- Proxy popularity of beer type by relative number of beer types per brewery.
- Opportunities for expansion
- Brewery density per capita
9 | Clean up Repository | TBD | NA |  | 2018-06-24
- Should be low effort
10 | Deliverables |  |  |  | 2018-06-24
1) R Markdown
2) R Code
3) Presentation

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only